Quarterly Report – Public Page

Date of Report: 1st Quarterly Report, December 29, 2022

Contract Number:  693JK32210009POTA

Prepared for: Government Agency: DOT and Co-funders

Project Title: Innovative Leak Detection Methods for Gas and Liquid Pipelines

Prepared by: Pipeline Research Council International, Inc.

Contact Information: Gary Choquette: gchoquette@prci.org phone: 402-915-5565

For quarterly period ending: January 10, 2022

1: Items Completed During this Quarterly Period:

| Item # | Task # | Activity/Deliverable | Title | Federal Cost | Cost Share |
| --- | --- | --- | --- | --- | --- |
| 1 | 1 | Kick-off web meeting with all the stakeholders | Meeting summary and action items included in the quarterly report | $3,980 | $3,980 |
| 2 | 1 | Quarterly Project Management & Status Update Reporting | Submit 1st quarterly report | $722 | $722 |

2: Items Not Completed During this Quarterly Period:

| Item # | Task # | Activity/Deliverable | Title | Federal Cost | Cost Share |
| --- | --- | --- | --- | --- | --- |

3: Project Financial Tracking During this Quarterly Period:

Note that this chart reflects Federal share only.

4:  Project Technical Status –

Activities and completion percentage is summarized in the following table:

| Payable Milestone | Item No. | Task No. | Activity/Deliverable | QuarterCode | %Complete | Note |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | 1 | Project kick off meeting and scope review | 2022Q4 | 100% | Completed |
| 1 | 2 | 1 | Quarterly project management & status update | 2022Q4 | 95% | Completed |
| 2 | 3 | 5 | Development of simulated systems with measurement errors and simulated leaks | 2023Q1 | 10% | Underway |
| 2 | 4 | 3 | Host site review checklist development | 2023Q1 | 35% | First draft underway |
| 2 | 5 | 1 | Literature review and compendium update | 2023Q1 | 5% | Underway |
| 2 | 6 | 2 | Inline flow measurement selection guidelines | 2023Q1 | 75% | Work is functionally complete, needs to be finalized. |

Additional information on tasks actively underway or completed this period:

- Items 1 and 2 are functionally completed with actual invoicing the only outlying task.

- Item 3: Development of a simulated system has been initiated.

- Item 4: work is progressing on preparing for a host site visit. Scheduling the host site visit is pending the completion on the non-disclosure agreement. Work on developing the host site checklist is actively underway.

- Item 5: A literature review is underway and will focus on both leak detection system gaps as well as reducing uncertainty in measurement accounting.

- Item 6: A guidance document to aid in the selection of inline flow measurement for system segmentation purposes is well underway and will be provided at the next quarterly update.

Overall, the project is estimated at 10% complete which is ahead of plan of 1.5% by end of Q1.

5: Project Schedule –

The project is ahead of schedule on a work completed basis. The project does run the risk of a delay should the non-disclosure agreement be executed in a timely manner.