2010 State Damage Prevention Program Grants Progress Report

Funding Opportunity Number:   DTPH56-10-SN-0001

CFDA Number: 20.720

Award Number: DTPH56-10-G-PHPS20

Project Title: Vermont Department of Public Service State Damage Prevention

Date Submitted: 12/6/10

Submitted by:

GC Morris 
Gas Engineer 
Vermont Dept. of Public Service 
112 State St. 
Montpelier, VT 05620-2601 
802-828-4073

Specific Objective(s) of the Agreement

Under this grant agreement, Vermont Department of Public Service will develop four damage prevention strategy documents: a communications plan, a quality assurance plan, an education plan, and a technology plan. The grantee will integrate these four plans with current initiatives to form a comprehensive statewide underground damage prevention strategy which addresses the nine elements and provides a mechanism for regular assessment of success metrics.

Workscope

Under the terms of this grant agreement, the Grantee will address the following elements listed in 49 USC

§60134 through the actions it has specified in its Application.

 Element (1): Participation by operators, excavators, and other stakeholders in the development and implementation of methods for establishing and maintaining effective communications between stakeholders from receipt of an excavation notification until successful completion of the excavation, as appropriate.

 Element (3): A process for reviewing the adequacy of a pipeline operator’s internal performance measures regarding persons performing locating services and quality assurance programs.

 Element (4): Participation by operators, excavators, and other stakeholders in the development and implementation of effective employee training programs to ensure that operators, the one call center, the enforcing agency, and the excavators have partnered to design and implement training for the employees of operators, excavators, and locators.

 Element (8): A process for fostering and promoting the use, by all appropriate stakeholders, of improving technologies that may enhance communications, underground pipeline locating capability, and gathering and analyzing information about the accuracy and effectiveness of locating programs.

Accomplishments for this period (Item 1 under Article IX, Section 9.01 Progress Report: “A comparison of actual accomplishments to the objectives established for the period.”)

Element I:

- A survey was distributed to contractors via direct mail and outreach at stakeholder events.  This survey was designed to gain knowledge about communication habits, online behavior and damage prevention training desires.  Survey results have been compiled and used to develop both a communications plan and a training plan.

- A draft communication plan has been developed based on survey responses, conversations with stakeholders, and capabilities of the Public Service Department.  This plan is currently under revision.

- Direct contact information has been gathered for one call center member companies and municipalities who operate water and/or sewer facilities who are not members of the one call center.  This information has been compiled into utility directory and a searchable database for non-member facility operators.

- A conference call was hosted with municipalities to discuss one call center membership, the appropriate response to a locate request from an excavator, and actions municipalities should take to protect their facilities such as installing tracer wire in all newly installed facilities and developing reliable maps of existing facilities.

- A new website devoted to underground utility damage prevention hosted by the Public Service Department is under development and 80% complete.  This site includes information regarding enforcement, utility contact information, training materials, online forms for event registration and damage reporting, and other resources for excavators such as a list of private utility locators, pre-excavation checklist, and a form for recording one call ticket information.

Element III

- A review of other state practices regarding locator QA has been performed to examine possible mechanisms for program implementation.

- Underground utility damage data for the past five years has been reviewed to determine the size and scope of locating deficiencies.

- A review of the state statutes has been performed to determine the authority of the Public Service Department to require facility operators to implement a quality assurance program according to a minimum standard developed by the PSD.  Based on this review a mechanism for QA program implementation has been proposed.

- Information requests have been submitted to all companies performing utility locates within the state to determine the number and features of quality assurance programs in place.

- A quality assurance template based on NULCA and CGA best practices has been developed and submitted to the stakeholder group, MUST, for review and comment.  Possible mechanisms for third party review of locator performance were discussed with MUST in an attempt to develop consensus among all parties on this issue.

Element IV

- Survey data was used to develop a training plan which is currently under revision.

- Outreach activities including attendance at MUST meetings, stakeholder events such as the Municipal Highway Show were used to gather input regarding development of additional training formats and topics.

- A series of training bulletins termed “Toolbox Trainings” have been developed in response to stakeholder input.  To date seven bulletins have been developed with two additional bulletins under development.

- In response to stakeholder input, a series of computer based training modules are under development to be hosted on the Public Service Department website.

Element VIII

- The Virtual Private DIRT damage reporting application from the Common Ground Alliance has been purchased and modifications made to allow data download into the case management system in use by the Public Service Department.

- Conversations with the state webmaster and information technology department have been held to identify resources available to the Public Service department to develop technology solutions to streamline the damage investigation process resulting in the discovery of a case management software package under development by other state agencies which could be adapted for Public Service Department needs.

Quantifiable Metrics/Measures of Effectiveness (Item 2 under Article IX, Section 9.01 Project Report: “Where the output of the project can be quantified, a computation of the cost per unit of output.”)

- 1071 surveys were distributed to contractors, excavators, landscapers, and other stakeholders via post mail to determine communication habits and training needs.  This mailing also included information about how to get involved in the stakeholder group MUST, and a series of damage prevention tips.  This survey was also distributed at the Municipal Highway Show.  To date 370 responses have been received.

- Information requests were submitted to 101 one call center member companies regarding direct contact information to be assembled into directory for stakeholders and locator quality assurance programs.

- Information request were sent to 267 municipalities in regards to the status of municipally owned or operated utilities and to establish a contact person for those utilities.

- Four outreach events have been held to gather input from the stakeholder community about what programs, applications, and other tools are desired to improve communication between stakeholders and encourage damage prevention training.

- 1134 damage incident records from 2003-2009 were reviewed for locator related root causes to determine the scope of location errors.

- Seven “Tool Box” training bulletins have been developed.

- Two computer based training modules have been developed.

Issues, Problems or Challenges (Item 3 under Article IX, Section 9.01 Project Report: “The reasons for slippage if established objectives were not met. “)

One member of the UVM team left the project in August, this in combination with the delayed award date have caused a revision to the number of outreach activities scheduled.  Originally 4-5 outreach meetings with excavators via meal functions or other events were planned.  These one time activities have been postponed or cancelled in favor of activities which will have a long term effect on the damage prevention program in Vermont.

Mid-term Financial Status Report

The mid-term financial report has been sent as a separate attachment to the AA

Plans for Next Period (Remainder of Grant)

In the time that remains, development of computer based training modules will continue with a target of six modules in total and an associated interactive quiz.  Website development will continue with modifications made in response to stakeholder feedback.  One additional stakeholder event is scheduled for December to review developed communications and training materials as well as revisit implementation of a locator quality assurance program.  The four comprehensive plans for communications, training, locator quality assurance, and technology implementation will be finalized.

Requests of the AOTR and/or PHMSA

No actions requested at this time.