2010 State Damage Prevention Program Grants Progress Report

Funding Opportunity Number:   DTPH56-10-SN-0001

CFDA Number: 20.720

Award Number:  DTPH56-10-G-PHPS05

Project Title:  Kansas Corporation Commission State Damage Prevention

Date Submitted:  March 31, 2011

Submitted by:  Leo Haynos, Robert Jackson

Specific Objective(s) of the Agreement

Under this grant agreement, the Kansas Corporation Commission will continue the successful pilot program begun in 2008 to augment the enforcement of the Kansas Underground Utility Damage Prevention Act.

Workscope

Under the terms of this grant agreement, the Grantee will address the following elements listed in 49 USC §60134 through the actions it has specified in its Application.

Element (7): Enforcement of State damage prevention laws and regulations for all aspects of the damage prevention process, including public education and the use of civil penalties for violations assessable by the appropriate State authority.

Accomplishments for this period (Item 1 under Article IX, Section 9.01 Progress Report: “A comparison of actual accomplishments to the objectives established for the period.”)

For Calendar year 2010, the Kansas Corporation Commission employed one FTE dedicated to damage prevention enforcement and education in the Wichita metropolitan area.  The inspector’s duties consist primarily of on-site field inspections of utility damage locations.  To perform this function, the inspector relies on real time reports of damages from two gas distribution utilities, one electric utility in the area as well as occasional reports from a cable TV company and telephone company.  Also, the One Call ticket database is monitored for emergency locate requests that may indicate facility damage has occurred.  As part of the onsite damage investigations, the damage prevention inspector issues citations for violations of the Kansas Underground Utility Damage Prevention Act and its associated regulations.  For Calendar year 2010, the Wichita damage prevention inspector has issued 15 notices of probable noncompliance to excavators and utility operators for various violations of Kansas law. These actions resulted in seven civil penalties being issued for a total of $3,500 in fines.   In addition to damage investigations, the inspector conducts other site investigations of locating activity.  In total, the inspector has performed 227 on-site investigations over 2010.  Because communication is an integral part of the damage prevention process, the inspector also dedicates a significant amount of time to education and training of excavators and facility operators.  In this time period, the KCC inspector initiated 123 tail gate safety meetings with onsite field crews at damage sites and 27 meetings with utility operators and other interested parties. With this grant a South Central Kansas common ground alliance chapter has been established and is now addressing local issues of interest and educating attendees on damage prevention.  Also worthy of noting is the seminar given by the KCC inspector to students of a community college enrolled in a heavy equipment operator training program.  This has become an annual event for the college.

Quantifiable Metrics/Measures of Effectiveness (Item 2 under Article IX, Section 9.01 Project Report: “Where the output of the project can be quantified, a computation of the cost per unit of output.”)

For the reporting period, the Wichita area generated 69,000 excavation locate requests or 15% of the Kansas statewide total.  There were 813 damages reported for the Wichita area.   Of this amount, 244 damages, (30% of total), were reported as damages to natural gas distribution facilities. Of the 244 damages to natural gas facilities, the KCC inspector performed an on site inspection for 162 (64%) of the natural gas facility damages.  Based on the locate requests received by the gas distribution operators in the Wichita area, this sector suffered 2.5 damages per 1,000 locate requests.  Although there is still room for improvement in this metric, it compares favorably to the telecommunications industry for the same area which appears to be approximately 5 damages per 1,000 locates requested.  We believe our enforcement and training presence in the construction activities of Wichita is beginning to lower the number of damages to the natural gas infrastructure when normalized by the number of locates requested.

Issues, Problems or Challenges (Item 3 under Article IX, Section 9.01 Project Report: “The reasons for slippage if established objectives were not met. “)

No issues or problems to date.

Financial Status Report

The financial report has been sent as a separate attachment to the AA.

Plans for Next Period

For the future of the grant, we expect to continue working on the above stated objectives.   In addition to on-site inspection and enforcement activities, we also plan to start working with the Wichita City Fire Department training them in how to interpret locate markings when responding to underground line strikes.  Also the KCC has put in place a focus on horizontal boring operations because we have identified this area as having a need to improve with respect to the use of reasonable care within the excavation tolerance zone.

Requests of the AOTR and/or PHMSA

No actions requested at this time.